## Web
Project Name: PriyoShop (Web) Sprint - 1 No. of Features: 9 No. of test Cases: 16 Total Bugs: 9
Test Case Run | 16 | Sprint 1 |  |  |  | Compo￼nent wise
Status | Count | %
Passed | 7 | 43.75% |  |  |  | Total Bugs | Web
Blocked | 0 | 0% |  |  |  | 19 | 9
Untested | 0 | 0%
Retest | 0 | 0%
Failed | 9 | 56.25%
| Severity | [5 empty] | Bug-Type
Component | Critical | Major | Minor | Low | Subtotal | Component | Functional | Visual | Performance | Crash | Subtotal
Web | 0 | 6 | 2 | 1 | 9 | Web | 9 | 0 | 0 | 0 | 9
Total | 0 | 6 | 2 | 1 |  | Total | 9 | 0 | 0 | 0 | 9
|  | Component vs Severity | [5 empty] | Component vs Bug-Type
Note on B3: Specify you test run ID from TestRail here

## App
Project Name: PriyoShop (App) Sprint - 1 No. of Features: 9 No. of test Cases: 16 Total Bugs: 10
Test Case Run | 16 | Sprint 1 |  |  |  | Compo￼nent wise
Status | Count | %
Passed | 6 | 37.5% |  |  |  | Total Bugs | Android
Blocked | 0 | 0% |  |  |  | 19 | 10
Untested | 0 | 0%
Retest | 0 | 0%
Failed | 10 | 62.5%
| Severity | [5 empty] | Bug-Type
Component | Critical | Major | Minor | Low | Subtotal | Component | Functional | Visual | Performance | Crash | Subtotal
Android | 0 | 7 | 2 | 1 | 10 | Android | 10 | 0 | 0 | 0 | 10
Total | 0 | 7 | 2 | 1 |  | Total | 10 | 0 | 0 | 0 | 10
|  | Component vs Severity | [5 empty] | Component vs Bug-Type
Note on B3: Specify you test run ID from TestRail here